## 2021 INITIATIVE
|  |  |  | Builders Corporation (BC) | [26 empty] | Recommended to Protect the sheet with a password (Menu>Review>Protect Sheet) | [6 empty] | INITIATIVE
2021 INITIATIVE & PERFORMANCE REPORT
Road Construction Project
| Initiative Description |  |  |  |  | Strategic Objectives | [11 empty] | P. Start Date |  |  | A. Start Date |  |  | P. End Date |  |  | A. End Date |  |  | T. P. Budget |  |  | T. Spent Bdgt |  |  | Init. Plan % |  |  | Init. Actual %
| Road Concept Design, Preliminary Engineering and Tenders preparation |  |  |  |  | - Develop network within time and specs - Optimize capital and operating expenditure - Ensure highest level of safety and reliability | [11 empty] | 2020-06-10 |  |  | 0 |  |  | 2021-09-05 |  |  | 0 |  |  | 13756606 |  |  | 1285310 |  |  | 100% |  |  | 67.95%
[18 empty] | - | [5 empty] | - | [5 empty] | -12471296 | [5 empty] | -32.05%
Initiative Team |  | Key Deliverables |  |  |  | Key Risks / Challenges | [9 empty] | Prob. | Impa. | Mitigation Plans | [11 empty] | Reporting Comments
Sp. | Julian Jones | Update Configuration Baseline |  |  |  | Change of BC the traffic forecasts | [9 empty] | Med | Med | Confirm the traffic forecast by end of July 2018 | [11 empty] | Baseline 4 Configuration has been agreed by the Board, contractual formalization on-going
Mgr. | Philippe Miller | Facilities Requirements |  |  |  | Delay in geotechnical and topographical surveys | [9 empty] | Low | Med | Close follow-up of the Engineer Progress and suppor to get NOCs | [11 empty] | GEO and TOPO sub-contract has been issued, work have started
Team Members | Michel Hegis | Concept Design and Preliminary Engineering |  |  |  | Delay in the tender packages preparation | [9 empty] | Low | High | Goint to Tender with Concept Design on 15 Nov and issue Addendum in December to include the PE | [11 empty] | Strategy agreed at COO/CEO Level and presented to Technical Committee and approved by the Board
| Sebastien Mofe | Network CAPEX |  |  |  | Increase of the Network CAPEX | [9 empty] | Med | High | Review the Engineer CAPEX and organize value engineering workshops | [11 empty] | In progress and related to the above
| Francis Kevin | Tendering Packages
Henry Emmy
Milestones |  | Weight (%) | Start Date | End Date | % | 2021 | [11 empty] | 2022 | [11 empty] | 2023
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Update Configuration Baseline 03 Report (traffic forecast) | 10% | 2018-07-01 | 2018-08-31 | Plan | 2021 3: 10%; 2021 4: 20%; 2021 5: 30%; 2021 6: 40%; 2021 7: 50%; 2021 8: 100%
|  |  | 2018-07-01 |  | Actual | 2021 3: 5%; 2021 4: 10%; 2021 5: 20%; 2021 6: 20%; 2021 7: 25%; 2021 8: 50%; 2021 9: 90%; 2021 10: 100%
|  |  | 0 | - | Variance | - | - | -5% | -10% | -10% | -20% | -25% | -50% | -10% | 0% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
2 | Topographical and Geotechnical Surveys | 5% | 2018-06-10 | 2019-03-31 | Plan | 2021 4: 5%; 2021 5: 6%; 2021 6: 7%; 2021 7: 10%; 2021 8: 30%; 2021 9: 50%; 2021 10: 60%; 2021 11: 70%; 2021 12: 100%
|  |  | 2018-06-10 |  | Actual | 2021 5: 4%; 2021 6: 2%; 2021 7: 1%; 2021 8: 1%; 2021 9: 5%; 2021 10: 15%; 2021 11: 40%; 2021 12: 60%
|  |  | 0 | - | Variance | - | - | - | - | -2% | -5% | -9% | -29% | -45% | -45% | -30% | -40% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
3 | O&M + Freight Facilities PE and related CAPEX | 20% | 2018-06-10 | 2019-01-09 | Plan | 2021 5: 5%; 2021 6: 5%; 2021 7: 5%; 2021 8: 10%; 2021 9: 30%; 2021 10: 50%; 2021 11: 70%; 2021 12: 85%; 2022 1: 100%
|  |  | 2018-06-10 |  | Actual | 2021 5: 4%; 2021 6: 4%; 2021 7: 1%; 2021 8: 2%; 2021 9: 8%; 2021 10: 15%; 2021 11: 35%; 2021 12: 50%
|  |  | 0 | - | Variance | - | - | - | - | -1% | -1% | -4% | -8% | -22% | -35% | -35% | -35% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
4 | Border Connection PE and related CAPEX | 5% | 2018-06-10 | 2018-12-31 | Plan | 2021 6: 5%; 2021 7: 5%; 2021 8: 30%; 2021 9: 50%; 2021 10: 75%; 2021 11: 95%; 2021 12: 99%; 2022 1: 100%
|  |  | 2018-06-10 |  | Actual | 2021 6: 2%; 2021 7: 1%; 2021 8: 20%; 2021 9: 30%; 2021 10: 75%; 2021 11: 95%; 2021 12: 99%
|  |  | 0 | - | Variance | - | - | - | - | - | -3% | -4% | -10% | -20% | 0% | 0% | 0% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
5 | Section PE and related CAPEX | 20% | 2018-06-10 | 2019-02-04 | Plan | 2021 7: 5%; 2021 8: 10%; 2021 9: 30%; 2021 10: 50%; 2021 11: 60%; 2021 12: 75%; 2022 1: 80%; 2022 2: 90%; 2022 3: 100%
|  |  | 2018-06-10 |  | Actual | 2021 7: 5%; 2021 8: 5%; 2021 9: 10%; 2021 10: 50%; 2021 11: 60%; 2021 12: 65%
|  |  | 0 | - | Variance | - | - | - | - | - | - | 0% | -5% | -20% | 0% | 0% | -10% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
6 | Update PE and related CAPEX | 10% | 2018-06-10 | 2018-12-10 | Plan | 2021 7: 5%; 2021 8: 30%; 2021 9: 50%; 2021 10: 75%; 2021 11: 80%; 2021 12: 90%; 2022 1: 95%; 2022 2: 95%; 2022 3: 100%
|  |  | 2018-06-10 |  | Actual | 2021 7: 1%; 2021 8: 13%; 2021 9: 40%; 2021 10: 60%; 2021 11: 70%; 2021 12: 75%
|  |  | 0 | - | Variance | - | - | - | - | - | - | -4% | -17% | -10% | -15% | -10% | -15% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
7 | Section PE and related CAPEX | 20% | 2018-06-10 | 2019-04-30 | Plan | 2021 8: 10%; 2021 9: 30%; 2021 10: 40%; 2021 11: 50%; 2021 12: 60%; 2022 1: 75%; 2022 2: 85%; 2022 3: 90%; 2022 4: 100%
|  |  | 2018-06-10 |  | Actual | 2021 8: 3%; 2021 9: 10%; 2021 10: 40%; 2021 11: 50%; 2021 12: 60%
|  |  | 0 | - | Variance | - | - | - | - | - | - | - | -7% | -20% | 0% | 0% | 0% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
8 | System Documentation Update | 10% | 2018-06-10 | 2019-02-28 | Plan | 2021 9: 30%; 2021 10: 50%; 2021 11: 60%; 2021 12: 75%; 2022 1: 80%; 2022 2: 85%; 2022 3: 85%; 2022 4: 90%; 2022 5: 95%; 2022 6: 100%
|  |  | 2018-06-10 |  | Actual | 2021 9: 10%; 2021 10: 50%; 2021 11: 60%; 2021 12: 75%
|  |  | 0 | - | Variance | - | - | - | - | - | - | - | - | -20% | 0% | 0% | 0% | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
9 |  |  |  |  | Plan
Actual
|  |  | - | - | Variance | bar: 2021 1 to 2023 12
10 |  |  |  |  | Plan
Actual
|  |  | - | - | Variance | bar: 2021 1 to 2023 12
Total |  | 100% | 2020-06-10 | 2021-09-05 | Plan | 0% | 0% | 1% | 2.25% | 4.3% | 5.6% | 8.25% | 22% | 41% | 57.25% | 68.25% | 80.45% | 88.5% | 93% | 96.5% | 99% | 99.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[5 empty] | Actual | 0% | 0% | 0.5% | 1% | 3% | 3.1% | 4.7% | 9.9% | 21.35% | 46.5% | 58.75% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95% | 67.95%
|  |  | - | - | Variance | 0% | 0% | -0.5% | -1.25% | -1.3% | -2.5% | -3.55% | -12.1% | -19.65% | -10.75% | -9.5% | -12.5% | -20.55% | -25.05% | -28.55% | -31.05% | -31.55% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05% | -32.05%
Budget |  | Opex/ Capex | Variance (AED) | Total (AED) | Plan / Spent | 2021 1: 2021; 2022 1: 2022; 2023 1: 2023
[6 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
1 | Engineer | CAPEX | -8710285 | 9814405 | Plan | 2021 7: 1683319; 2021 10: 3402327; 2022 1: 3158454; 2022 4: 1570305
|  |  |  | 1104120 | Spent | 2021 7: 0; 2021 10: 1104120
2 | PMC | CAPEX | -3761011 | 3942201 | Plan | 2021 7: 676147; 2021 10: 1366630; 2022 1: 1268672; 2022 4: 630752
|  |  |  | 181190 | Spent | 2021 7: 0; 2021 10: 181190
3 |  |  | 0 | 0 | Plan
|  |  |  | 0 | Spent
4 |  |  | 0 | 0 | Plan
|  |  |  | 0 | Spent
5 |  |  | 0 | 0 | Plan
|  |  |  | 0 | Spent
Total |  |  | -12471296 | 13756606 | Plan | 2021 1: 0; 2021 4: 0; 2021 7: 2359466; 2021 10: 4768957; 2022 1: 4427126; 2022 4: 2201057; 2022 7: 0; 2022 10: 0; 2023 1: 0; 2023 4: 0; 2023 7: 0; 2023 10: 0
|  |  |  | 1285310 | Spent | 2021 1: 0; 2021 4: 0; 2021 7: 0; 2021 10: 1285310; 2022 1: 0; 2022 4: 0; 2022 7: 0; 2022 10: 0; 2023 1: 0; 2023 4: 0; 2023 7: 0; 2023 10: 0
[7 empty] | Actual/Spent | [5 empty] | Plan | [5 empty] | On Track |  | 0% or better |  |  |  | Delay |  | -1% to -20% |  |  |  | Off Track |  | -21% or Worse | [5 empty] | Error
Note on G5: List the strategic objective(s) that this initiative is supporting
Note on S5: Planned START Date for the whole initiative DD-MM-YYYY
Note on V5: Actual START Date for the whole initiative DD-MM-YYYY
Note on Y5: Planned END Date for the whole initiative DD-MM-YYYY
Note on AB5: Actual END Date for the whole initiative DD-MM-YYYY
Note on AE5: Total Planned Budget for the whole initiative (AED)
Note on AH5: Total SPENT Budget (Cumulative) for the whole initiative (AED)
Note on AK5: Total Planned Completion % for the whole initiative (%) Cross time
Note on AN5: Total Actual CUMULATIVE Completion % for the whole initiative (%) Cross time
Note on S7: START Date VARIANCE for the whole initiative Variance: (+) Positive Days = Delayed Start (-) Negative Days = Started Early
Note on Y7: END Date VARIANCE for the whole initiative Variance: (+) Positive Days = Delayed (-) Negative Days = Finished Early
Note on AE7: Variance based on cumulative initiative budget vs spent
Note on AK7: % left to complete the initiative (cross years)
Note on A9: Add sponsor, manager, and team members names here
Note on C9: List the initiative key deliverables (outcomes)
Note on G9: list all main key risks or challenges that might affect the completion of this initiative on time and budget This list could be changed or updated during the reporting phase as well
Note on Q9: PROBABILITY of happening: Select from: High Medium Low
Note on R9: What will be the IMPACT if happened: Select from: High Medium Low
Note on S9: For each main risk, list your mitigation plans to avoid or decrease the risk impact / probability. This list could be changed or updated during the reporting phase.
Note on AE9: to be used to reflect any other infomartion and comments during quarterly reporting period
Note on A10: Sponsor name
Note on A11: Manager name
Note on A17: Only includes milestone that begins in 2018
Note on C17: Total should = 100%
Note on D17: DD-MM-YYYY Variance: (+) Positive Days = Delayed Start (-) Negative Days = Started Early
Note on E17: DD-MM-YYYY Variance: (+) Positive Days = Delayed (-) Negative Days = Finished Early
Note on C49: Should = 100%
Note on D49: Planned START Date for the whole initiative DD-MM-YYYY
Note on E49: Planned END Date for the whole initiative DD-MM-YYYY
Note on F49: Cumulative Plan % (by Month) (Weights have to be there for the formula to work)
Note on D50: Actual START Date for the whole initiative DD-MM-YYYY
Note on E50: Actual END Date for the whole initiative DD-MM-YYYY
Note on F50: Cumulative Actual % (by Month) (Weights have to be there for the formula to work)
Note on D51: START Date VARIANCE for the whole initiative Variance: (+) Positive Days = Delayed Start (-) Negative Days = Started Early
Note on E51: END Date VARIANCE for the whole initiative Variance: (+) Positive Days = Delayed (-) Negative Days = Finished Early
Note on F51: Variance between planned % and actual % for this month
Note on C53: Select between OPEX and CAPEX
Note on D53: - AED (under budget) + AED (over budgets)
Note on E53: Formulas only
Note on D65: Variance based on cumulative initiative budget vs spent

## 2021 Graphs
[15 empty] | Builders Corporation (BC) | [41 empty] | Recommended to Protect the sheet with a password (Menu>Review>Protect Sheet) | [7 empty] | INITIATIVE
2021 INITIATIVE PERFORMANCE REPORT IN GRAPHS
| Road Construction Project | [27 empty] | Plan Budget: |  |  | 13756606 |  |  | Spent Budget: |  |  |  |  | 1285310 |  |  | Sponsor: |  |  | Julian Jones | [10 empty] | Manager: |  |  | Philippe Miller
MILESTONES | 1 | Update Configuration Baseline 03 Report (traffic forecast) | [12 empty] | 2 | Topographical and Geotechnical Surveys | [12 empty] | 3 | O&M + Freight Facilities PE and related CAPEX | [12 empty] | 4 | Border Connection PE and related CAPEX | [12 empty] | 5 | Section PE and related CAPEX
|  | - | - | -5% | -10% | -10% | -20% | -25% | -50% | -10% | 0% | - | - |  |  | - | - | - | - | -2% | -5% | -9% | -29% | -45% | -45% | -30% | -40% |  |  | - | - | - | - | -1% | -1% | -4% | -8% | -22% | -35% | -35% | -35% |  |  | - | - | - | - | - | -3% | -4% | -10% | -20% | 0% | 0% | 0% |  |  | - | - | - | - | - | - | 0% | -5% | -20% | 0% | 0% | -10%
|  | Start Date VAR: |  |  | 0 |  | End Date VAR: |  | - |  | (Days) |  | W: | 10% |  | Start Date VAR: |  |  |  | 0 | End Date VAR: |  | - |  | (Days) |  | W: | 5% |  | Start Date VAR: |  |  |  | 0 | End Date VAR: |  | - |  | (Days) |  | W: | 20% |  | Start Date VAR: |  |  | 0 |  | End Date VAR: |  | - |  | (Days) |  | W: | 5% |  | Start Date VAR: |  |  | 0 |  | End Date VAR: |  | - |  | (Days) |  | W: | 20%
| ENG (CH2M) have mobilized and working with PMC. ER Commercial Dept, is required to finalize Traffic Forecast by end July | [13 empty] | TOPO and GEO Contract Awarded, No progress report avail yet | [13 empty] | Work have started and meeting are taking place between PMC / ENG, but no submittal received yet | [13 empty] | Work have started and meeting are taking place between PMC / ENG, but no submittal received yet | [13 empty] | Work have started and meeting are taking place between PMC / ENG, but no submittal received yet
| 6 | Update PE and related CAPEX | [12 empty] | 7 | Section PE and related CAPEX | [12 empty] | 8 | System Documentation Update | [12 empty] | 9 | 0 | [12 empty] | 10 | 0
|  | - | - | - | - | - | - | -4% | -17% | -10% | -15% | -10% | -15% |  |  | - | - | - | - | - | - | - | -7% | -20% | 0% | 0% | 0% |  |  | - | - | - | - | - | - | - | - | -20% | 0% | 0% | 0% |  |  | - | - | - | - | - | - | - | - | - | - | - | - |  |  | - | - | - | - | - | - | - | - | - | - | - | -
|  | Start Date VAR: |  |  | 0 |  | End Date VAR: |  | - |  | (Days) |  | W: | 10% |  | Start Date VAR: |  |  |  | 0 | End Date VAR: |  | - |  | (Days) |  | W: | 20% |  | Start Date VAR: |  |  |  | 0 | End Date VAR: |  | - |  | (Days) |  | W: | 10% |  | Start Date VAR: |  |  | - |  | End Date VAR: |  | - |  | (Days) |  | W: | 0% |  | Start Date VAR: |  |  | - |  | End Date VAR: |  | - |  | (Days) |  | W: | 0%
| Work have started and meeting are taking place between PMC / ENG, but no submittal received yet | [13 empty] | Work have started and meeting are taking place between PMC / ENG, but no submittal received yet | [13 empty] | Work have started and meeting are taking place between PMC / ENG, but no submittal received yet | [13 empty] | Note: | [13 empty] | Note:
BUDGET VS SPENT | 1 | Engineer | [12 empty] | 2 | PMC | [12 empty] | 3 | 0 | [12 empty] | 4 | 0 | [12 empty] | 5 | 0
|  |  |  | P. Budget |  |  | Bdgt. Spent |  | Variance | [8 empty] | P. Budget |  |  | Bdgt. Spent |  | Variance | [8 empty] | P. Budget |  |  | Bdgt. Spent |  | Variance | [8 empty] | P. Budget |  |  | Bdgt. Spent |  | Variance | [8 empty] | P. Budget |  |  | Bdgt. Spent |  | Variance
|  |  |  | 9814405 |  |  | 1104120 |  | -8710285 |  |  |  | (AED) |  |  |  |  | 3942201 |  |  | 181190 |  | -3761011 |  |  |  | (AED) |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | (AED) |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | (AED) |  |  |  |  | 0 |  |  | 0 |  | 0 |  |  |  | (AED)
| Note: Two ENG Invoices related to PE are in the process of approval. It will be reflected in Q4. | [13 empty] | Note: PMC didn't submit any invoice regarding PE review. | [13 empty] | Note: | [13 empty] | Note: | [13 empty] | Note:
[17 empty] | Actual/Spent | [5 empty] | Plan | [7 empty] | On Track |  |  | 0% or better |  |  | Delay |  |  |  | -1% to -20% |  |  |  | Off Track |  | -21% or Worse